## Sheet1
Acme Robotics Human Detector-Tracker
ID | Task | Estimated Time(minutes)
1 | Plan Phase 1
1.1 | Literature survey | 120
1.2 | Comparing various architecture and framework | 60
1.3 | Collecting/finalizing dataset | 60
1.4 | Defining assumptions and deliverables | 30
1.5 | Discusing potential risks and plan | 30
1.6 | Setting up stubs and unit tests for the code | 120
1.7 | Building repository with Travis | 10
1.8 | Reviewing UML diagrams | 30
1.9 | Implementing initial code for design | 120
1.1 | Code Analysis using cppcheck and cpplint | 30
1.11 | Updating documents | 40
1.12 | Discussion of future implementation | 60
1.13 | Updating documents | 30
2 | Implementing Phase 2
2.1 | Revise UML diagram | 15
2.2 | Revise code | 30
2.3 | Implement code as per activity diagram | 180
2.4 | Code Analysis using cppcheck and cpplint | 30
2.5 | Update documents | 30
2.6 | Make implemention video | 60
2.7 | Generate doxygen documentation | 10
2.8 | Verify build using travis and coveralls | 15
2.9 | Push code to github | 10